## ShipSafe Tasks
Task ID | File | Line | Bug | Severity | Fix Suggestion | Status
C01 | frontend (git diff) |  | Breaking API change in diff | HIGH | No action required — check passed | OK
C02 | frontend/package.json |  | Manifest known-CVE artifact | CRITICAL | No action required — check passed | OK
C03 | requirements.txt |  | requirements.txt / lockfile CVE | HIGH | No action required — check passed | OK
C04 | frontend/.env |  | VAULT_ID missing from config | CRITICAL | No action required — check passed | Pending
C05 | frontend/.env |  | Hardcoded secret in config | CRITICAL | No action required — check passed | OK
C06 | frontend/.env |  | Actuator / debug endpoint wildcard exposed [N/A for react] | INFO | No action required — check passed | OK
C07 | frontend/.env |  | No TLS/HTTPS configured | HIGH | Add server.ssl.* properties and configure a keystore for HTTPS | Pending
C08 | frontend/package.json |  | No security middleware/dependency | HIGH | Add spring-boot-starter-security to pom.xml and create a SecurityFilterChain bean | Pending
C09 | frontend/package.json |  | No DB migration tool | MEDIUM | Add flyway-core or liquibase-core to pom.xml for managed schema migrations | Pending
C10 | src/Dockerfile |  | Dockerfile exposes privileged port (<1024) | MEDIUM | No action required — check passed | OK
C11 | pipeline.yaml |  | Hardcoded S3 bucket in pipeline.yaml | HIGH | No action required — check passed | OK
C12 | notebook.ipynb |  | Notebook contains api_key literal | MEDIUM | No action required — check passed | OK
C13 | notebook.ipynb |  | Notebook hardcoded local CSV path | LOW | No action required — check passed | OK
C14 | pipeline.yaml |  | GPU env var (CUDA_VISIBLE_DEVICES) missing | LOW | Add CUDA_VISIBLE_DEVICES env var to pipeline.yaml GPU job definition | Pending
C16 | deploy/codeengine.yaml |  | VAULT_ID missing from deploy/codeengine.yaml | CRITICAL | No action required — check passed | Pending
C15 | frontend/package.json |  | Phantom / invalid dependencies in manifest | INFO | No action required — check passed | OK